## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comments
42952 | 17/EM/0005 | 215706 | CARD 4983 GALACTIC-HF | Range Agreed | 5 | 15 | Not Available / Not Agreed |  |  | 2019-06-14 | 3 | Recruitment Finished | This was a difficult study due to eligibility criteria e.g. enrolment of potential participants after coming off IV furosemide, however, once the heart failure patient comes off IV furosemide they get discharged due to bed pressures, we had a short screening period to enrolment, , after the amendment it became a bit better. So far we had 5 screen failures and 3 randomised. Reached its target globally. Trial is closed to recruitment but has 3-4 years follow up period.
42953 | 16/SW/0120 | 201715 | Optalyse PE | Number Agreed | 8 | 8 | Date Agreed | 2019-08-31 | 5 | 2019-05-01 | 5 | Recruitment Finished | Sponsor closed recruitment to study early due to issues with recruiting in the UK, especially scarcity of beds
42954 | 17/EE/0034 | 218200 | Astral-3 | Range Agreed | 4 | 20 | Date Agreed | 2018-03-31 | 2 | 2019-05-31 | 2 | Recruitment Finished | 2 of 4 recruited for period of study. Target not met due to rare disease. Trial extended internationally as slow to meet targets