## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Patient Recruited? | Date of First Patient Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Patient Recruited | Duration between Date Site Selected and First Patient Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
140903 | 16/EE/0190 | 200804 | Prepare-ABC | yes | 2018-09-18 | 13 | 40 | 53 | 2018-04-11 | 2018-07-27 | 2016-04-25 | 2018-07-27 | 2018-08-09 |  | 2018-08-16 |  | N/A
140904 | 17/WS/0210 | 231280 | ALLEGRO | yes | 2019-01-31 | 86 | 85 | 171 | 2018-07-24 | 2018-08-13 | 2018-04-27 | 2018-11-05 | 2018-11-07 |  |  | Within Sponsor Company (Comments - Initiating required) | Did not receive contract from sponsor for signatures until November 2018. With two sponsors involved, there is delay with the sponsor issuing green light. | Sponsor
140905 | 18/SC/0242 | 238151 | BLING III study | yes | 2018-12-04 | 44 | 102 | 146 | 2018-03-05 | 2018-07-11 | 2018-08-23 | 2018-07-11 | 2018-08-24 |  | 2018-11-30 | Sponsor Delay | NHS provider given 2 days notice from sponsor to attend the SIV in Dublin. When unable to attend, had to arrange another SIV. | Sponsor
140906 | 17/LO/0334 | 214459 | FLO-ELA | yes | 2019-01-14 | 68 | 6 | 74 | 2017-07-12 | 2018-11-01 | 2017-03-29 | 2019-01-07 | 2019-01-08 |  | 2019-01-10 | Staff availability issues | PI off sick 2-3 months. Trainee anesthetists deliver the study. They move site every 6 months which made it difficult for them to train and start the study. | NHS Provider
140907 | 18/SC/0454 | 249509 | POISE-3 | yes | 2019-03-26 | 8 | 7 | 15 | 2019-01-16 | 2019-03-11 | 2019-01-16 | 2019-03-05 | 2019-03-19 |  | 2019-03-19
142682 | 18/SC/0222 | 223737 | NeoCLEAR | yes | 2019-02-01 | 16 | 7 | 23 | 2018-12-13 | 2019-01-09 | 2018-06-12 | 2019-01-24 | 2019-01-25 |  | 2019-01-29
144402 | 19/SC/0016 | 250165 | EMPRESS | no |  | 61 |  |  | 2019-02-08 | 2019-03-22 | 2019-02-01 | 2019-05-10 | 2019-05-22 |  | 2019-05-28
144414 | 17/NW/0512 | 221775 | PETReA | no |  | 232 |  |  | 2018-01-19 | 2018-09-17 | 2017-11-08 | 2019-05-01 | 2019-05-07 |  | 2019-05-08
144431 | 17/NE/0061 | 215780 | CONVINCE | no |  |  |  |  | 2017-11-01 | 2019-02-27 | 2017-07-25
153537 | 18/SC/0454 | 249509 | POISE-3 | Yes | 2019-04-01 | 8 | 13 | 21 | 2019-01-16 | 2019-03-11 | 2019-01-16 | 2019-03-05 | 2019-03-19 | Please Select... | 2019-03-19 |  | The date of first recruit input originally was the date consented and not recruited (randomised) | Please Select...
153538 | 18/SC/0222 | 223737 | NeoCLEAR | Yes | 2019-02-01 | 16 | 7 | 23 | 2018-12-13 | 2019-01-09 | 2018-06-12 | 2019-01-24 | 2019-01-25 | Please Select... | 2019-01-29 |  |  | Please Select...
153539 | 19/SC/0016 | 250165 | Empress | Yes | 2019-07-16 | 61 | 55 | 116 | 2019-02-08 | 2019-03-22 | 2019-02-01 | 2019-05-10 | 2019-05-22 | Please Select... | 2019-05-28 | F - No patients seen | Patients screened but delayed due to unavailability of eligible patients. Sponsor caused contracting delays nationally | Sponsor
H - Contracting delays
153540 | 17/ne/0061 | 215780 | convince | yes | 2019-11-22 | 121 | 147 | 268 | 2017-11-01 | 2019-02-27 | 2017-07-25 | 2019-06-04 | 2019-06-28 | Please Select... | 2019-08-12 | D - Sponsor Delays | Sponsor delay for amendment required for Change in PI | Sponsor
153541 | 19/EM/0258 | 266702 | Fluids Exclusively Enteral from Day 1 (FEED1) | No |  |  |  |  | 2019-08-07 | 2019-09-18 | 2019-09-13 |  |  | Site declined to participate |  |  | Discussions were underway between Sponsor and local clinical team about the concerns on the design of the study and BFI accreditation upon receipt of the protocol. Meanwhile, the Local information pack was received from sponsor before a decision was made locally to decline the study based on Sponsor clarifications. This resulted in a default status as 'site selected' | Please Select...
153542 | 18/SS/0085 | 243640 | Alpha-2 agonists for sedation (A2B Trial) | No |  | 278 |  |  | 2018-07-09 | 2019-01-18 | 2018-12-14 | 2019-10-10 | 2019-10-23 | Please Select... |  | E - Staff availability issues F-No Patients Seen | Queries regarding excess treatment costs and funding. Set-up restarted in August 2019. The staff went on maternity leave and there was shortage of staff cover. | NHS Provider
153543 | 17/SS/0082 | 222441 | SoSTART | No |  | 167 |  |  | 2018-08-26 | 2019-02-06 | 2017-10-05 | 2019-07-05 | 2019-07-23 | Please Select... | 2019-09-05 | D - Sponsor Delays | 'Original delay in Study set-up locally after site selection in February 2019. Delay since June 2019 from Sponsor's legal team to sort the contract . | Both
153546 | 19/nw/0158 | 259931 | Surgery or Cast for Injuries of the EpicoNdyle in Childrens Elbows | Yes | 2019-08-01 | 69 | 44 | 113 | 2019-04-08 | 2019-04-10 | 2019-03-25 | 2019-05-21 | 2019-06-18 | Please Select... | 2019-06-19 | A- Permissions delayed/denied D-sponsor delays | Delay with sponsor and site due to lack of suitable SIV dates | Both
153548 | 19/lo/0236 | 230338 | Effort | No |  | 22 |  |  | 2019-11-03 | 2019-11-03 | 2019-07-01 | 2019-11-29 | 2019-11-25 | Please Select... | 2019-12-04 |  |  | Please Select...